Event Planning Guide

Looking Ahead -

Life After High School

Countdown Timetable to Seminar

Three to six months in advance:

- Schedule the event in consultation with whoever is in charge of event-planning for tenth graders. You may want to consult local school calendars as well.

- Discuss with teen leaders and/or pastors and schedule a blessing event to take place during a worship service at church or at a youth activity sometime soon after this event.

- Reserve the room(s) to be used.

Two months in advance:

- Create a publicity strategy and timeline. Options to consider:

  - Letter (See sample under publicity on CD)

  - Email (See sample under publicity on CD)

  - Mail out special invitations

  - Social media (Facebook, youth leader’s blog, etc.)

  - Text messages to parents (See sample under publicity on CD)

  - Web site

  - Verbal announcement(s) in church – endorsed by the pastor if possible

  - Bulletin announcement(s)

  - Notes/flyers that students take home

  - Posters

  - Create a fun video or skit and present it at a youth activity a few weeks prior to the seminar

  - Phone-calling team -- Each caller could choose the tenth grade families they will contact to maximize pre-existing relationships

  - Make and show a blessing object to promote the event (See Blessing Object folder on CD.)

- Decide if you will serve a meal and who will organize it.

- Establish a budget. Determine how much the event will cost per family. Decide how much to charge families that participate.

- Decide whether the printing of blessing object characteristic traits will be done in house or you will be ordering a digital printed version @ $4.95 per print plus shipping and handling. To order go to susanfun@cox.net. (See Blessing Object folder on CD.)

Six weeks in advance:

- Develop a publicity plan. Choose a registration deadline so character traits can be printed and meal arrangements taken care of in time (at least a week before the seminar date, two weeks if ordering digital prints of character traits).

- Choose a community building strategy that will get kids and adults interacting and laughing together. (See suggestions below.)

- Decide on facility arrangements (table cloths, center pieces, arrangement of tables in the room, etc.)

Four weeks in advance:

- Begin publicizing the event to tenth grade families.

- Send out registrations.

- Reserve room for the seminar and media equipment needed such as sound system, DVD player, projector and screen for the presentation.

Two weeks in advance:

- Organize registrations

- Print character traits for students on vellum paper for the registrations turned in.

- Order digital printed character traits if not making at seminar (Registration deadline needs to be two weeks prior to the event.)

One week in advance:

- Continue printing character traits for 10th graders on vellum paper as registrations arrive.

- Finish room décor arrangements.

- Print the handouts and gather supplies, pens, pencils, markers, name tags, etc… (see “Materials Needed” below)

Community Building:

Creating a Foundation for Meaningful Dialog

With the right introductory activities, you will be able to help everyone relax at the event and “go with the flow.” Below are several ideas for developing a relaxed atmosphere. Don’t short-change this component! It’s very important!

- Serve a meal. It doesn’t have to be fancy. Pizza is a great kid-friendly meal that can be added to the cost of the event for a modest amount.

- Create a party atmosphere. Simple décor additions can make the room warm and inviting. Have contemporary Christian music playing as families arrive. (Make sure it’s a music style that 10th graders will appreciate!)

- Get them laughing. This is critical! Here are some possibilities:

  - Hold a “best-looking legs” contest – Dads hide behind a sheet, roll up their pant legs and remove their shoes and socks. Moms and kids judge the dads’ legs while the dads’ upper bodies are hidden behind the sheet. (And/or have the moms and kids pick whose legs that belong to their husband/dad…)

  - Have a shoe-kick contest. It’s surprising how hard it is to kick a shoe for distance. Some will kick so hard the shoes go backwards over their heads. (Everyone has to line up side by side and kick at the same time for this to work best.)

  - Have a balloon stomp contest. Everybody takes their shoes off, then blows up a balloon and ties it to their ankle so that the balloon trails onto the floor. At the leader’s signal, everybody attempts to pop everyone else’s balloon by stomping on it with their bare feet. If your balloon is popped or dislodged from your ankle, you’re out of the game. Last one standing wins.

  - Recognize the winner(s) with a prize, or letting them get dessert first or take their picture and post it in the 10th grade Youth Room for a few weeks.

- Instead of a game, do a group-building exercise that allows table groups to work together. See the Community Builder activity “Fish in Clips” in Leading the Event.

A Word About Leadership

Whether this is a stand-alone event or part of the Faith Legacy Series in your setting, we recommend a key strategic principle of leadership: Don’t do this alone.

Don’t assume you have to do everything yourself. Invite some friends to be a part of the leadership team! (One great way to do this would be to have 11th grade parents who experienced this event last year host this year’s seminar for 10th grade families.) Here are some roles/responsibilities that will help everyone’s load be a little lighter:

| Task | Person(s) Responsible |
| --- | --- |
| Up front leader for the event (emcee) – someone who is comfortable in front of people and can set them at ease, get them laughing. See community building suggestions and Leading the Event. |  |
| Meal coordinator/team – menu design, catering contact, pizza delivery, shopping for groceries, etc. |  |
| Publicity/invitations coordinator (refer to list above) |  |
| Register – track registrations and order 31 Biblical Virtues bookmarks, for each family registered. This can be ordered from www.kidskountpublishing.com. Give character traits for each student to the blessing object coordinator to print. Email one week prior to seminar reminding participants to bring frames and 5x7 scrapbook paper. |  |
| Retreat materials – run off copies of all handouts – a nice touch is to have all paper resources and pencils in folders for families to take home with them. Gather all materials listed below under “Materials Needed”. |  |
| Host team – Greet families as they arrive, help people create name tags, help serve the meal, stay after to clean up. Decorations – table cloths & table decor, lighting, center pieces, etc. |  |
| Blessing object coordinator – print character traits for each 10th grader from registrations on vellum paper or order digital trait prints (see Blessing Object on CD). At the seminar, give directions on how to assemble. |  |

Finances / Budget

As you create a budget for this event, consider the following:

- food

- decorations

- community building activity supplies

- invitations

- mailings

- markers

- name tags

- “Biblical Virtues” bookmarks

- supplies to make the blessing object

- printing costs for handouts

- folders for handouts

Some of these expenses can be covered by your church’s or organization’s operating budget. Two financial principles to consider:

- You don’t want finances to prevent families from participating.

- People value the things they invest in.

With these principles in mind, consider the following:

- Charge a modest fee that most families can easily afford.

- Receive a free will offering.

- Invite a donor or a group of donors to underwrite a portion of the experience.

- Include the event in the church budget, while still charging families a small registration fee.

- Clearly state in your publicity materials that there is financial support for families whose budgets are tight. No one should miss this event due to their family finances.

- Do not serve a meal. This will cut down on costs and on the seminar time frame, but it might make community building a bit more challenging. Eating together tends to set people at ease in a very natural way.

Materials Needed

- nametags

- markers

- vellum paper and vellum tape if families make the blessing objects at the seminar

- digital printed character traits for each student (option: if not making at the seminar)

- paper cutters (several)

- participants handouts including your church’s calendar of faith steps for the year

- folders

- paper clips and straws (community builder)